## Sheet1
Risk	Statement	Response	Objective	Likelihood	Impact	Risk Level		Likelihood / Impact	Insignificant	Negligible	Moderate	Extensive	Significant
Connection Issues	Access to the internet could prevent both learning and troubleshooting	Always have something I can be getting on with if offline	Stay productive	Possible	Moderate	5		Almost Certain	5	6	7	8	9
Tunnel Vision	Focusing too much on getting one small detail working at the cost of other more important things	Regular sanity checks. Is it worth continuing for now or moving on to something else?	Deliver complete application	Possible	Moderate	5		Likely	4	5	6	7	8
Lose time to learning	As I’m trying to learn new things to implement in this project, I need to make sure I have enough time to actual create everything.	Planned periods of time for learning	Deliver complete application	Unlikely	Moderate	4		Possible	3	4	5	6	7
Computer issues unrelated to project	As this is my only available laptop, losing usage of it would make it very difficult to complete the project	It’s always been reliable so far, but can arrange borrowing one if needed, and regular git commits would make continuing very easy.	Be able to work at all	Plausible	Very Significant	5		Unlikely	2	3	4	5	6
Losing focus after long stretches of working	It’s easy to stay working for too long at once which can then impact the rest of the day	Take regular breaks even if they don’t feel needed.	Stay productive	Likely	Moderate	6		Plausible	1	2	3	4	5
Using unfamiliar packages/techniques	Unfamiliar features can require lots of learning or result in an easily breakable application	Learn new concepts thoroughly (keeping an eye on time)	Keep application functional	Unlikely	Extensive	5